## budget
Total Budget	5000000

	%	K	Num Tasks
Widening	70	3500	15
NTUA	30	1050	5
TUC	10	350	2
UNIWA	5	175	1
Akdeniz	15	525	2
TotalView	5	175	1
VUGTK	20	700	3
STU	15	525	2
	100	3500

Budget Per WP	%
WP1 Institutional Reform	10-15
WP2 Upskilling	20-25
WP3 Research Excellence	25-30
WP4 Digital Transformation	20-25
WP5 Outreach	5-10

Clusters (or Focus Areas)
Earth System Modeling	NTUA
Geohazards	Akdeniz
Environmental & Climate	TUC or STU
Space Exploration	VUGTK

## WP1
Task 1.1 CoARA-aligned Research Assesment

NTUA	Coordinate task, develop initial CoARA framework / Pilot internally and adjust framework based on experience / Provide structured guidance (templates, best practices)
TUC	Full implementation of the framework / Provide detailed feedback for refining the framework / Participate in workshops/trainings
Akdeniz	Pilot implementation (relevant to context) / Participate in workshops/trainings

Indicative Workflow	1. NTUA leads the initial development of the CoARA aligned assessment framework / 2. NTUA develops, pilots and refines the framework internally / 3. TUC simultaneously pilots and provides detailed feedback for further refinement / 4. Akdeniz integrates selected elements of the framework relevant to context / 5. After pilots and refinements the framework is submitted to the Executive Committee and evaluated by the Research Panel / 6. Recommendations from the Research Panel are incorporated / 7. The Governing Board approves and institutionalizes the final framework / The Research Panel annualy evaluates widening partners based on the framework

Task 1.2 Establishing a Research Management and Administration Unit

Note: The RMA office should be probably incorporated in the organization chart!

NTUA	Create a fully functional central RMA office as a model / Develop standards,te mplates and management protocols / Participate in workshops/trainings / Conduct staff training for RMA (for other institutes)
VUGTK	Establish or significantly upgrade existing RMA capabilities / Participate in NTUA-led training, fully integrate standards
Akdeniz	Strenghten existing RMA capabilities / Adopt key RMA standards from NTUA-led model selectively

Task 1.3 Creating Interdisciplinary Research Clusters

Note: The clusters should align with our focus areas

NTUA	Coordinates establishment of clusters with CoE strategy
NTUA	Leads the Earth System Modeling cluster (research activities, outputs, meetings, collaboration, reporting)
Akdeniz	Leads the Geohazards Cluster
TUC or STU	Leads the Environment and Climate Cluster
VUGTK	Leads the Space Exploration Cluster

## WP2
Task 2.1 Staff Exchange

NTUA	Coordinates exchanges on behalf of widening partners / Identifies priority areas for capacity building / Prepares candidates for outgoing mobility / Tracks impact and integration of returned stuff
All Widening Institutes	Send early career researchers, technical staf and scientists for training according to role
Non Widening Partners	Host researchers and provide training

Task 2.2 Training in Research Management, Intellectual Property Rights and Open Science
NTUA	Participates in training with focus on Management / Supports internal integration of open science policies / Aligns training with CoE’s CoARA aligned assessment goals
UNIWA	Participates in training with focus on Intellectual Property Rights
STU	Participates in training with focus on Open Science
Non Widening Partners	Host researchers and provide training

Task 2.3 Entrepreneurial and Science Communication Training
TotalView	Designs and delivers practical entrepreneurship workshops / Leads communication skills training / Provides real-world case studies and mentors
NTUA	Host workshops / Participates in training / Integration into research strategy
UNIWA	Participate in training
VUGTK	Participate in training

## WP3
Task 3.1 Shared Research Infrastructure

NTUA	Coordinates infrastructure inventory and integration / Leads infrastructure upgrade plans and usage protocols / Shares infrastructure
Akdeniz	Shares infrastructure / Helps in integration
VUGTK	Shares infrastructure / Helps in integration / Performs tests
GFZ	Provides expert guidance on infrastructure integration (Q&A, best practices)

Task 3.2 Joint Research and Innovation Agenda

NTUA	Coordinates the development of the agenda / Organizes yearly strategic workshops / Provide input as lead of Earth System Modeling
Akdeniz	Leads Geohazards cluster, provide input
TUC or STU	Provide input as leads of the Environment and Climate Cluster
VUGTK	Provide input as lead of the Space Exploration Cluster
Non Widening Partners	Advide on scientific trends and funding landscape / Help align the agenda with ERA, ESA, Copernicus, etc

Task 3.3 Seed Projects for Collaborative Research

Non Widening Partners	Support teams with guidance, review, and quality assurance / Participate as co-authors
Cluster leaders	Coordinate, design and launch at least one collaborative project

## WP4
Task 4.1 AI for Geodesy and Research Management

UNIWA	Coordinate AI applications for research management (call detection, scheduling, NLP assistance, etc) / Pilots automation tools for internal workflows
NTUA	Coordinates AI applications for geodesy
Cluster Leaders	Explore AI tools and ideas for respective fields / Frame ideas, test pilots

Task 4.2 Digital Infrastructure Upgrade

TUC	Lead infrastructure audit and upgrade plan / Test new solutions (HPC, cloud tools, remote access platforms, etc) / Coordinates integration in CoE
NTUA	Provides central access infrastructure and initial models/pilots
Akdeniz	Tests upgraded connectivity, hybrid learning environments, remote access facilities, efficiency
UNIWA	Implements and tests CoE-wide collaboration tools / Focus on education and remote access platforms

Task 4.3 Data Science and Centralized Data Management

NTUA	Builds and maintains the central CoE data platform / Migrates critical data to cloud storage (e.g. GNSS) / Defines data governance and FAIR compliance strategy / Trains partners
Cluster Leaders	Overview and implement transition to advanced digital infrastructure
Non Widening	Advice on FAIR data implementation, metadata schemas, GDPR

## WP5
Task 5.1 Industry & Regional Innovation Linkages

TotalView	Coordinates, chairs the Entrepreneurship & Innovation Panel / Maps regional industry actors & clusters / Organizes matchmaking events and living-labs demos
Cluster Leaders	Map and engage stakeholders

Task 5.2 Citizen & Policy Engagement

TotalView	Design engagement formats & campaigns / Produce videos/visuals, social media stratey / Lead citizen-science tooling
NTUA	Host flagship events / Operate central website
Cluster Leads	Create living labs, tours, surveys and events (open days)

Task 5.3 Internationalisation & scientific Visibility

NTUA	Draft annual internationalisation plan / Coordinate memberships (IAG, GGOS, EUREF, etc) / Organize meetings with international actors
Cluster Leaders	Drive cluster diplomacy / Map and engage with international actors / Host bilateral events / Secure and maintain roles